## Summary
COMMERCIAL EVALUATION SUMMARY — Northgate Retail Centre
Date: 12 Jul 2026 ¦ From: Daniel Cross, Apex PM ¦ Project: Northgate Retail Centre ¦ Ref: APEX-COM-NRC-TP-003
Project | Northgate Retail Centre
Type of Work | Facade & Building Envelope Package
Facade Envelope Area | 5,800 m2
Procurement Type | Subcontractor ¦ 3 bidders ¦ Stage: 1st Submission
Currency | USD
SUMMARY PRICE BREAKDOWN (1st Submission)
BOQ Section | BuildRight Facades | Vertex Envelope | Clad-Tech Systems
A Preliminaries & Site Establishment
B Design, Engineering & Testing
C Unitised Curtain Wall
D Stick Glazing & Shopfronts
E Rainscreen Cladding
F Spandrel, Fire-rating & Smoke Seals
G Louvres, Canopies & Specialist Items
H Facade Access & Maintenance Interface
TOTAL PRICE (as submitted)
LEVELLING ADJUSTMENTS (from Levelling Schedule)
Total scope adjustments
NORMALISED COMPARISON (levelled, like-for-like)
Metric | BuildRight Facades | Vertex Envelope | Clad-Tech Systems
Normalised Total
Rate per m2 (levelled)
Price Ranking (levelled)
Spread (highest vs lowest)
RECOMMENDATION
After levelling for BuildRight's scope exclusions (+ c.$491k), BuildRight Facades remains the lowest normalised bid at c.$4.80M — about $508k (10.6%) below Vertex Envelope and $952k (19.8%) below Clad-Tech. TWO SCENARIOS: (A) If BuildRight confirms the four excluded items at or near the levelled add-back, award to BuildRight subject to closing the life-safety scope gaps (fire-rating, PMU, BMU) in the subcontract. (B) If clarifications reveal further scope or BuildRight cannot firm up fire-rating/PMU/BMU pricing, award to Vertex Envelope — strongest technical, fully compliant, no scope gaps, at a defensible c.$5.31M. Clad-Tech Systems is not price-competitive but its 14-week programme advantage should be tabled at PTM #14 if the transfer-slab delay compresses the facade window.
COMMERCIAL RISK FLAGS
# | Risk | Category | Impact | Bidder | Detail
1 | Fire-rating & smoke seals excluded | Scope Gap | HIGH | BuildRight | 2hr spandrel + perimeter barrier not priced (c.$271k). Code / life-safety requirement.
2 | PMU testing excluded | Scope Gap | MEDIUM | BuildRight | Air/water/structural/seismic test omitted ($95k). Mandatory for system warranty.
3 | Facade access (BMU interface) excluded | Scope Gap | MEDIUM | BuildRight | Restraint anchors & tracks not priced ($125k). Interface with main contractor.
4 | Signage / feature-lighting under-priced | Cost | MEDIUM | BuildRight | $45k vs $68k–$82k (82% spread). Likely scope under-interpretation.
5 | Elevated preliminaries | Commercial | LOW | BuildRight | Prelims c.12.9% of price vs 7–10% norm — mild front-loading; confirm access strategy.
6 | Highest price, fastest programme | Schedule | LOW | Clad-Tech | 14-week faster completion; c.$444k premium over Vertex. Assess time-value.
7 | Strongest technical, mid price | Commercial | LOW | Vertex | No scope gaps; fully compliant. Lowest risk-adjusted option.
NEXT ACTIONS
# | Action | Owner | Date | Priority | Status
1 | Issue scope-gap clarification (fire-rating, PMU, BMU) to BuildRight |  | Daniel Cross | 16 Jul 2026 | High | Open
2 | Request BuildRight rate build-up for signage / lighting scope |  | James Okafor | 16 Jul 2026 | Medium | Open
3 | Confirm fire-rating & PMU as mandatory with Studio Arc / FormWorks |  | Maria Santos | 15 Jul 2026 | High | Open
4 | Verify BuildRight prelims / access strategy (front-loading) |  | Cost Bureau | 17 Jul 2026 | Medium | Open
5 | Assess programme value of Clad-Tech acceleration vs cost premium |  | Daniel Cross | 18 Jul 2026 | Medium | Open
6 | Finalise levelling once clarifications returned |  | Cost Bureau | 20 Jul 2026 | High | Open
7 | Present combined TP-002 + TP-003 recommendation at PTM #14 |  | Daniel Cross | 18 Jul 2026 | High | In Progress
STATUS LEGEND
Open | Not yet started
In Progress | Work underway
Awaiting | Waiting on another party
Complete | Done and accepted
Closed | No further action

## Detailed BOQ
COMMERCIAL EVALUATION — DETAILED BOQ — Northgate Retail Centre
Facade & Building Envelope Package ¦ 1st Submission ¦ Currency: USD ¦ Ref: APEX-COM-NRC-TP-003
Item | Description | Qty | Unit | BuildRight Rate | BuildRight Total | Vertex Rate | Vertex Total | Clad-Tech Rate | Clad-Tech Total | Lowest Total | Spread % | Flag
Section A | Preliminaries & Site Establishment
A1 | Site establishment, offices & welfare facilities | 1 | Sum | 165000 |  | 185000 |  | 205000
A2 | Facade access — mast climbers, hoists & MEWPs | 1 | Sum | 120000 |  | 135000 |  | 150000
A3 | Site management & specialist supervision | 16 | month | 11500 |  | 12800 |  | 14000
A4 | Temporary protection, propping & logistics | 1 | Sum | 85000 |  | 95000 |  | 105000
Section A subtotal
Section B | Design, Engineering & Testing
B1 | Shop drawings, BIM coordination & samples | 1 | Sum | 165000 |  | 195000 |  | 210000
B2 | Structural / thermal calculations & PE certification | 1 | Sum | 85000 |  | 105000 |  | 115000
B3 | Performance mock-up (PMU) fabrication | 1 | no | 120000 |  | 145000 |  | 160000
B4 | PMU testing — air / water / structural / seismic | 1 | no | 0 |  | 95000 |  | 105000
Section B subtotal
Section C | Unitised Curtain Wall
C1 | Unitised curtain wall to primary retail frontage | 1950 | m2 | 585 |  | 640 |  | 660
C2 | Feature corner & fin units | 260 | m2 | 720 |  | 785 |  | 860
C3 | Entrance structural glass feature | 140 | m2 | 1250 |  | 1380 |  | 1520
Section C subtotal
Section D | Stick Glazing & Shopfronts
D1 | Stick-system curtain wall to upper levels | 1150 | m2 | 420 |  | 465 |  | 505
D2 | Aluminium shopfront / mall entrance glazing | 520 | m2 | 385 |  | 420 |  | 455
D3 | Automatic sliding entrance assemblies | 5 | no | 18500 |  | 21000 |  | 23500
Section D subtotal
Section E | Rainscreen Cladding
E1 | ACM / aluminium rainscreen to solid elevations | 1500 | m2 | 245 |  | 268 |  | 292
E2 | Terracotta rainscreen to feature elevations | 400 | m2 | 395 |  | 430 |  | 470
E3 | Insulation, breather membrane & support subframe | 1900 | m2 | 62 |  | 70 |  | 78
Section E subtotal
Section F | Spandrel, Fire-rating & Smoke Seals
F1 | Fire-rated spandrel panels (2-hour) | 640 | m2 | 0 |  | 285 |  | 310
F2 | Perimeter fire barrier & smoke seals | 1850 | lm | 0 |  | 48 |  | 54
F3 | Insulated spandrel panels (non-rated) | 720 | m2 | 155 |  | 168 |  | 182
Section F subtotal
Section G | Louvres, Canopies & Specialist Items
G1 | Architectural louvres & plant screens | 380 | m2 | 340 |  | 375 |  | 410
G2 | Entrance canopy & feature soffit cladding | 260 | m2 | 420 |  | 460 |  | 500
G3 | Signage zones & feature lighting integration | 1 | Sum | 45000 |  | 68000 |  | 82000
Section G subtotal
Section H | Facade Access & Maintenance Interface
H1 | BMU restraint anchors, tracks & tie-offs | 1 | Sum | 0 |  | 125000 |  | 145000
H2 | Mullion-guided cradle interface | 1 | Sum | 38000 |  | 55000 |  | 62000
H3 | Cleaning, handover & O&M manuals | 1 | Sum | 28000 |  | 34000 |  | 40000
Section H subtotal
GRAND TOTAL (1st Submission)

## Levelling Schedule
LEVELLING SCHEDULE — Northgate Retail Centre
Scope-normalisation adjustments (from TP-002 findings) ¦ Currency: USD ¦ Ref: APEX-COM-NRC-TP-003
# | Adjustment Description | Source of Estimate | Levelling Method | Status | BuildRight Adj | Vertex Adj | Clad-Tech Adj
1 | PMU testing (air/water/structural/seismic) excluded by BuildRight | Vertex Envelope BOQ item B4 | Add back to BuildRight | Applied |  | 0 | 0
2 | Fire-rated spandrel panels (2-hour) excluded by BuildRight | Vertex Envelope BOQ item F1 | Add back to BuildRight | Applied |  | 0 | 0
3 | Perimeter fire barrier & smoke seals excluded by BuildRight | Vertex Envelope BOQ item F2 | Add back to BuildRight | Applied |  | 0 | 0
4 | BMU restraint anchors & tracks (facade access) excluded by BuildRight | Vertex Envelope BOQ item H1 | Add back to BuildRight | Applied |  | 0 | 0
5 | Signage / feature-lighting scope appears under-priced by BuildRight | Delta vs Vertex/Clad-Tech (item G3) | Pending clarification | Open | 0 | 0 | 0
6 | Clad-Tech 14-week programme acceleration (time-value not priced) | Bidder programme submission | No adjustment — noted | Noted | 0 | 0 | 0
TOTAL ADJUSTMENTS