## Design Tracker
NORTHGATE RETAIL CENTRE — CONSULTANT DESIGN TRACKER
Project: | Northgate Retail Centre |  |  |  | Report Date: | 10 Jul 2026
Location: | Brownfield city-centre site |  |  |  | Report No.: | W37 / Month 9
Consultants: | Studio Arc (Architect) · FormWorks (Structural) |  |  |  | Prepared / CM: | Apex Project Management
Design Manager: | Maria Santos (Apex PM) |  |  |  | Period Ending: | 10 Jul 2026
MILESTONE TRACKER
Milestone | Phase | Baseline Date | Forecast Date | Variance (days) | Status | Type | Priority | Predecessor | Comment
STUDIO ARC — ARCHITECTURAL
100% DD Architectural Package | DD | 2026-05-15 | 2026-05-15 |  | Complete | Submission | High | Concept design freeze | Issued & accepted; basis for CD production.
Building Permit — Architectural Amendment | Permits | 2026-06-20 | 2026-06-18 |  | Complete | Approval | High | 100% DD Architectural | Amendment approved by authority 18 Jun.
CD Package — Zone A (Retail Mall) | CD | 2026-06-30 | 2026-07-04 |  | On Track | Submission | High | 100% DD Architectural | Issued Rev C, 4-day slip; Meridian tenant comments incorporated.
Facade GA & Setting-Out Drawings | CD | 2026-07-04 | 2026-07-18 |  | At Risk | Submission | Critical | Facade subcontract award | Held pending facade subcontractor selection; drives cladding procurement.
CD Package — Zone B (Anchor Units) | CD | 2026-07-25 | 2026-07-25 |  | On Track | Submission | Medium | CD Zone A | On programme; anchor tenant fit-out interface confirmed.
Reflected Ceiling Plans L1–L3 | CD | 2026-08-08 | 2026-08-08 |  | On Track | Submission | Medium | MEP coordination model | Awaiting Flow Systems services routing sign-off.
Door & Ironmongery Schedule | CD | 2026-08-15 | 2026-08-15 |  | On Track | Submission | Low | CD Zone A/B | Draft in progress; no issues.
FORMWORKS — STRUCTURAL
100% DD Structural Package | DD | 2026-05-15 | 2026-05-16 |  | Complete | Submission | High | Concept design freeze | Issued & accepted; 1-day slip absorbed.
Foundation & Basement CD | CD | 2026-06-06 | 2026-06-06 |  | Complete | Submission | High | 100% DD Structural | Issued on baseline; construction underway.
Superstructure CD — Zone A | CD | 2026-06-27 | 2026-06-30 |  | On Track | Submission | High | Foundation & Basement CD | Received; under Apex review, comments due 15 Jul.
Level 3 Transfer Slab — Design & Details | CD | 2026-06-27 | 2026-07-11 |  | Delayed | Submission | Critical | Superstructure CD Zone A | 14 days late — on CRITICAL PATH; blocked by DEC-018 (client loads) & RFI-041 (MEP clash). Slab pour cannot start until issued.
Transfer Slab — Temporary Works / Propping | CD | 2026-07-11 | 2026-07-25 |  | Delayed | Submission | Critical | L3 Transfer Slab Design | Knock-on from slab-design slip; propping design required before formwork.
Rebar Bending Schedules — L1/L2 | CD | 2026-07-18 | 2026-07-18 |  | On Track | Submission | Medium | Superstructure CD Zone A | On programme.
Structural Steel Connection Details | CD | 2026-08-01 | 2026-08-01 |  | On Track | Submission | Medium | Superstructure CD Zone A | Draft underway; no issues.
SUBMISSION LOG
Document Name | Rev | Submitted Date | Due Date | Status | Comments
AR-CD-ZA-100 — CD Zone A (Retail Mall) | C | 2026-07-04 | 2026-06-30 | Submitted | Studio Arc — 4-day slip; incorporates Meridian tenant comments.
ST-CD-ZA-100 — Superstructure Zone A | A | 2026-06-30 | 2026-06-27 | Submitted | FormWorks — under Apex review, comments due 15 Jul.
ST-CD-L3-100 — L3 Transfer Slab GA & Details | B |  | 2026-06-27 | Overdue | FormWorks — 14 days overdue, critical path; chased 08 & 10 Jul.
AR-CD-FAC-100 — Facade GA Package | — |  | 2026-07-04 | Overdue | Studio Arc — held pending facade subcontract award.
ISSUE / RFI / DECISION REGISTER
Ref | Description | Raised By | Date Raised | Status | Target Date | Owner | Comments
DEC-018 | Confirm Level 3 podium column transfer loads (retail tenant loading) | FormWorks | 2026-06-20 | Escalated | 2026-07-11 | Meridian Land | On critical path — blocks transfer-slab design issue.
RFI-041 | Transfer slab depth vs MEP riser clash at grid F/7 | Flow Systems | 2026-06-25 | Open | 2026-07-14 | FormWorks | Coordination sign-off required before slab GA can be released.
RFI-039 | Facade fixing zone / slab-edge tolerance | Studio Arc | 2026-06-30 | In Progress | 2026-07-16 | FormWorks | Dependent on facade subcontractor selection.
ISS-024 | Basement waterproofing spec vs Cornerstone VR (~$180k) | Cornerstone | 2026-07-02 | Open | 2026-07-18 | Apex PM | Apex disputes ~$70k; see commercial review.
TWO-WEEK LOOKAHEAD
Activity | Start | End | Owner | Dependencies | Status
Issue L3 transfer-slab design (Rev B) | 2026-07-11 | 2026-07-15 | FormWorks | DEC-018 client sign-off | In Progress
Resolve RFI-041 slab / MEP clash | 2026-07-11 | 2026-07-14 | FormWorks / Flow Systems | Coordination model | In Progress
Apex review of Superstructure Zone A CD | 2026-07-11 | 2026-07-15 | Apex PM | ST-CD-ZA received | Planned
Facade subcontract award (enables facade GA) | 2026-07-14 | 2026-07-14 | Apex PM | TER / commercial eval | Planned
Studio Arc issue Facade GA package | 2026-07-15 | 2026-07-22 | Studio Arc | Facade award | Blocked
Transfer-slab temporary works / propping design | 2026-07-16 | 2026-07-25 | FormWorks | L3 slab design issued | Planned
RESOURCE & COORDINATION
Item | Details | Action Required | Owner | Target Date
FormWorks resourcing | Additional structural engineer added to clear transfer-slab backlog | Confirm sustained through Zone B CD | FormWorks (Tom Whitfield) | 2026-07-18
Design coordination meeting | Weekly structural/MEP clash review — grids E–H, Level 3 | Hold mid-week ahead of PTM #14 | Apex PM (Maria Santos) | 2026-07-15
Facade interface | Studio Arc / structural fixing zones unresolved pending subcontractor | Close out at facade kickoff | Apex PM (Daniel Cross) | 2026-07-22