MINUTES OF MEETING

| Field | Content |
| --- | --- |
| Meeting Title | Project Team Meeting (PTM) #13 |
| Project | Northgate Retail Centre (3-level retail + mixed-use, ~42,000 m²) — Month 9 of 22 |
| Date | 09 Jul 2026 |
| Time | 10:00 – 11:45 (1 hr 45 min) |
| Location | Site Project Office, Meeting Room 1 / MS Teams (hybrid) |
| MOM Reference | NRC/MOM/2026/013 |
| Prepared by | Daniel Cross, Project Director, Apex Project Management |
| Distribution | All attendees + Meridian Land management copy |

ATTENDEES

| S.N. | Name | Company / Role | Email | Attendance |
| --- | --- | --- | --- | --- |
| 1 | Daniel Cross | Apex Project Management, Project Director (Chair) | daniel.cross@apexpm.com | Present |
| 2 | Maria Santos | Apex Project Management, Design Manager | maria.santos@apexpm.com | Present |
| 3 | James Okafor | Apex Project Management, Construction Manager | james.okafor@apexpm.com | Present |
| 4 | Priya Nair | Studio Arc, Lead Architect | priya.nair@studioarc.com | Present |
| 5 | Tom Whitfield | FormWorks Engineering, Structural Lead | tom.whitfield@formworks-eng.com | Present |
| 6 | Elena Duarte | Cornerstone Construction, Contracts Manager | elena.duarte@cornerstone-con.com | Present |
| 7 | [CONFIRM: name] | Meridian Land, Development Manager |  | Present |
| 8 | [CONFIRM: name] | Cost Bureau, Commercial Lead (QS) |  | Present |
| 9 | [CONFIRM: name] | Flow Systems, MEP Lead |  | Apologies |
| TO COPY |  |  |  |  |
| 1 | [CONFIRM: name] | Meridian Land, Project Sponsor |  |  |
| 2 | [CONFIRM: name] | Cornerstone Construction, Project Manager |  |  |

PREVIOUS MOM ACTIONS REVIEW (PTM #12 – 25 Jun 2026)

| # | Action | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 12-01 | FormWorks to issue IFC design for the Level 3 transfer slab. | Tom Whitfield | 02 Jul 2026 | Carried Forward |
| 12-02 | Cornerstone to submit substantiation back-up for the basement waterproofing variation. | Elena Duarte | 03 Jul 2026 | Open |
| 12-03 | Cost Bureau to circulate the levelled commercial comparison for the façade tenderers. | Cost Bureau | 01 Jul 2026 | Closed |
| 12-04 | Apex to close out the wet-weather delay assessment from the prior month. | James Okafor | 07 Jul 2026 | Carried Forward |

DISCUSSION AND ACTIONS

| ITEM NO. | DESCRIPTION | ACTION BY | ACTION DUE | REMARKS |
| --- | --- | --- | --- | --- |
| 1.0 | PROGRAMME STATUS & PROGRESS SLIP |  |  |  |
| 1.1 | Apex reported overall progress at 44% actual against 47% planned as at the Month 9 cut-off — a 3-point slip. Daniel Cross confirmed the slip is driven by two factors: (i) the Level 3 transfer-slab design delay (item 2.0) holding the superstructure sequence, and (ii) wet weather in the prior month affecting basement and groundworks output. |  |  | For information |
| 1.2 | James Okafor advised that a two-week recovery narrative is being prepared, targeting resequencing of fit-out enabling works to claw back schedule float independent of the transfer slab. James Okafor to issue the recovery narrative and revised look-ahead to the meeting. | James Okafor | 16 Jul 2026 | Action required |
| 1.3 | Meridian Land requested that any consequential completion-date impact be quantified separately from the recovery measures. Apex noted the request; assessment to follow the transfer-slab IFC issue (item 2.2). |  |  | Noted |
| 2.0 | STRUCTURAL DESIGN – LEVEL 3 TRANSFER SLAB (CRITICAL PATH) |  |  |  |
| 2.1 | Tom Whitfield (FormWorks) confirmed the Level 3 transfer-slab design is running two weeks behind the design programme, following additional analysis of transfer-beam deflection and a coordination clash with the MEP riser layout. The meeting noted the slab pour now sits on the project critical path. |  |  | For information |
| 2.2 | FormWorks committed to issue the IFC (Issued for Construction) transfer-slab package — previously carried forward from PTM #12 (action 12-01). Tom Whitfield to issue IFC drawings and the reinforcement schedule. | Tom Whitfield | 16 Jul 2026 | Action required |
| 2.3 | Priya Nair (Studio Arc) confirmed the architectural setting-out is unaffected and will not gate the IFC issue. Studio Arc to countersign the coordinated riser penetrations within 3 days of receiving the FormWorks package. | Priya Nair | 21 Jul 2026 | Action required |
| 2.4 | Elena Duarte (Cornerstone) stated that, subject to receiving IFC by 16 Jul, Cornerstone can hold the pour slot in the week commencing 27 Jul and will confirm the resequenced pour date and any acceleration cost. Cornerstone reserved its position on an extension of time pending the design issue. | Elena Duarte | 23 Jul 2026 | Action required |
| 2.5 | Apex recorded that the critical-path and any EOT entitlement will be assessed once IFC is received; Maria Santos to update the critical-path analysis and issue Apex's preliminary delay position. | Maria Santos | 24 Jul 2026 | Action required |
| 3.0 | FAÇADE PACKAGE PROCUREMENT |  |  |  |
| 3.1 | Apex reported the façade subcontract package is in final evaluation across three tenderers: BuildRight Facades (lowest price, with noted scope gaps), Vertex Envelope (mid price, strongest technical submission), and Clad-Tech Systems (highest price, fastest programme). Cost Bureau confirmed the levelled comparison from PTM #12 (action 12-03) is complete. |  |  | For information |
| 3.2 | The meeting agreed that, on best-value grounds — technical compliance weighted against the scope-gap risk in the lowest bid — Vertex Envelope is the preferred tenderer, subject to a final commercial confirmation of the levelled position. Decision recorded. |  |  | Decision recorded |
| 3.3 | Cost Bureau to finalise the levelled commercial comparison, confirming the add-back for BuildRight's scope gaps, so the price ranking is on a like-for-like basis. | Cost Bureau | 17 Jul 2026 | Action required |
| 3.4 | Daniel Cross to issue the façade award recommendation to Meridian Land for approval, on receipt of the finalised levelling. | Daniel Cross | 21 Jul 2026 | Action required |
| 4.0 | COMMERCIAL – BASEMENT WATERPROOFING VARIATION |  |  |  |
| 4.1 | Cornerstone tabled variation request VR-024 for revised basement waterproofing, valued at approximately $180,000. Elena Duarte stated the revision responds to a design change in the tanking specification and that the full amount is a legitimate entitlement. |  |  | For information |
| 4.2 | Apex disputed approximately $70,000 of the claim, its position being that the disputed portion covers waterproofing to the lift pits and construction joints that is already included within Cornerstone's contract scope and priced in the original bill. Both positions are recorded; the difference remains unresolved. |  |  | Noted |
| 4.3 | Cost Bureau to issue a formal assessment of VR-024, isolating the disputed ~$70,000 element against the contract scope and pricing document. | Cost Bureau | 22 Jul 2026 | Action required |
| 4.4 | Cornerstone to provide the detailed measurement and pricing back-up for VR-024 — outstanding from PTM #12 (action 12-02) — to allow the assessment to conclude. | Elena Duarte | 18 Jul 2026 | Action required |
| 5.0 | ANY OTHER BUSINESS & NEXT MEETING |  |  |  |
| 5.1 | No other business was raised. The meeting confirmed PTM #14 will proceed as scheduled (see NEXT MEETING), with the transfer-slab IFC status and the façade award as standing lead items. |  |  | Noted |

ACTIONS SUMMARY

| # | Action | Owner | Due Date | Priority |
| --- | --- | --- | --- | --- |
| 001 | Issue two-week recovery narrative and revised look-ahead programme. | James Okafor | 16 Jul 2026 | HIGH |
| 002 | Issue IFC transfer-slab drawings and reinforcement schedule (critical path). | Tom Whitfield | 16 Jul 2026 | CRITICAL |
| 003 | Countersign coordinated riser penetrations within 3 days of FormWorks package. | Priya Nair | 21 Jul 2026 | MEDIUM |
| 004 | Confirm resequenced transfer-slab pour date and any acceleration cost. | Elena Duarte | 23 Jul 2026 | HIGH |
| 005 | Update critical-path analysis and issue Apex preliminary delay/EOT position. | Maria Santos | 24 Jul 2026 | HIGH |
| 006 | Finalise levelled façade commercial comparison with scope-gap add-back. | Cost Bureau | 17 Jul 2026 | HIGH |
| 007 | Issue façade award recommendation (Vertex Envelope) to Meridian Land. | Daniel Cross | 21 Jul 2026 | HIGH |
| 008 | Issue formal assessment of VR-024 isolating the disputed ~$70k element. | Cost Bureau | 22 Jul 2026 | HIGH |
| 009 | Provide detailed measurement and pricing back-up for VR-024. | Elena Duarte | 18 Jul 2026 | MEDIUM |

NEXT MEETING

| Field | Content |
| --- | --- |
| Meeting | Project Team Meeting (PTM) #14 |
| Date | 15 Jul 2026 |
| Time | 10:00 – 11:30 |
| Location | Site Project Office, Meeting Room 1 / MS Teams (hybrid) |
| Agenda items | Transfer-slab IFC status & recovery; façade award confirmation; VR-024 waterproofing assessment; progress vs recovery programme. |

SIGN-OFF

Prepared by: Daniel Cross | Project Director | Apex Project Management

Date issued: 09 Jul 2026

Please review and advise of any amendments within 3 working days of issue. Silence will be taken as acceptance of these minutes as a true and accurate record.

Note: [CONFIRM: …] tags mark attendee names to be verified before issue.