## Instructions
PROCUREMENT TRACKER --- How To Use
Read this first. Keep it brief. Ask the Procurement Lead if anything is unclear.
WHAT THIS TRACKER DOES
Purpose |  | Back-plans procurement milestones from construction programme dates using 10 standard procurement stages. Shows which packages are on track, at risk, or behind.
Updated by |  | Construction Manager (weekly). Reviewed by Project Director.
Single entry point |  | All data is entered on the Procurement Schedule tab. The Dashboard auto-populates. Do not edit the Dashboard directly.
HOW TO FILL IT IN
Step 1 |  | Go to the Procurement Schedule tab. Each package occupies a Planned row (white/grey) and an Actual row (yellow).
Step 2 |  | For each work package, fill in: WP# (B), Package Description (C), Proc Route (D), Est Value (E), Priority (F), Required On Site (R), and Status (S).
Step 3 |  | Stage dates (columns H-Q) auto-calculate from Required On Site + Route + Value. Do not overwrite unless you have a specific reason.
Step 4 |  | As procurement progresses, fill in actual dates on the yellow Actual row underneath each package. Delta will calculate automatically.
Step 5 |  | Log any procurement risks on the Issues & Risks tab with owner and due date.
PROCUREMENT ROUTES
Route | Full Name | When to Use | Duration (>$5M) | Duration ($2-5M) | Duration (<$2M)
CT | Competitive Tender | Standard route. Full process: bid docs, RFP, competitive bids, evaluation, board approval. | ~15 wks | ~12 wks | ~8 wks
NQ | Negotiated Quotation | Packages under $2M, or urgent works under 60 calendar days. Shortened process. | - | - | ~8 wks
SS | Sole Source | Only one viable supplier (proprietary, OEM, continuity). No competitive process. | ~5.5 wks | ~5.5 wks | ~5.5 wks
MC | Main Contractor | Package procured through the main contractor's supply chain, not directly. MC manages the process. | Varies | Varies | Varies
Effect on tracker |  | Changing the Route dropdown changes which duration column is used from the Configuration sheet. This recalculates all stage dates automatically.
APPROVAL THRESHOLDS (auto-calculated on Dashboard)
Value Range | Approval Level | What This Means
>$30M | Board | Full tender board review. Book sessions early; group multiple packages in one session where possible.
$5M - $30M | Committee | Procurement committee. Shorter lead time but still needs scheduling.
$2M - $5M | Proc Head | Direct approval by the Procurement Head. Fastest formal route.
<$2M | Proc Manager | Direct approval by the Procurement Manager.
COLOUR CODING
RAG (auto) |  | Red = procurement start date has passed (will delay site). Amber = less than 30 days until procurement must start. Green = 30+ days. N/A = awarded or complete.
Delta (auto) |  | Positive number (red) = behind programme. Zero (green) = on programme. Negative (green) = ahead of programme.
Row shading |  | White/grey = Planned dates (auto-calculated, can override). Yellow = Actual dates (manual entry).
WHAT NOT TO EDIT
The following are formula-driven. Editing them will break the tracker:
Schedule |  | Stage dates (H-Q) on Planned rows, Float (T), Delta (U). These are formulas. If you need to override a date, clear the cell first.
Dashboard |  | Everything. The entire Dashboard sheet is formulas referencing the Schedule.
Configuration |  | Do not insert or delete rows 7-16. These are referenced by the auto-calc formulas.

## Procurement Schedule
PROCUREMENT SCHEDULE --- Northgate Retail Centre, Meridian Land development
Date: 12 Jul 2026 ¦ Ref: NGRC-PT-001 ¦ Rev: 0 ¦ Construction Manager: James Okafor ¦ THIS IS THE PRIMARY INPUT SHEET
Enter packages here. Stage dates (H-Q) AUTO-CALCULATE from Required On Site (R) + Proc Route (D) + Est Value (E). To override a date, clear the formula and type your date. Dashboard auto-populates from this sheet. Yellow rows = Actual dates (fill as procurement progresses).
# | WP# | Package Description | Proc Route | Est Value ($M) | Priority | P / A | Prep Bid Docs | Float RFP | Bid Period | Bid Review | Inter- views | Technical Eval | Approval / Award | Issue PO | Issue Contract | Mobili- sation | Required On Site | Status | Float (Days) | Overall Delta (Days) | Comments
1 | 0010 | Structural steel - transfer slab & primary frame | CT | 4.2 | High | Planned | 2026-06-23 | 2026-07-03 | 2026-07-10 | 2026-07-24 | 2026-07-31 | 2026-08-04 | 2026-08-11 | 2026-08-18 | 2026-08-25 | 2026-09-01 | 2026-09-15 | In Progress | -19 | 5
[6 empty] | Actual | 2026-06-28
2 | 0020 | Facade & unitised curtain wall | CT | 6.8 | High | Planned | 2026-06-21 | 2026-07-05 | 2026-07-12 | 2026-08-02 | 2026-08-12 | 2026-08-19 | 2026-08-29 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-10-05 | In Progress | -21 | -3
[6 empty] | Actual | 2026-06-18
3 | 0030 | Lifts & escalators | CT | 3.5 | High | Planned | 2026-10-23 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-11-30 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-15 | Not Started | 103
Actual
4 | 0040 | MEP services (mechanical, electrical, plumbing) | CT | 8.5 | High | Planned | 2026-08-17 | 2026-08-31 | 2026-09-07 | 2026-09-28 | 2026-10-08 | 2026-10-15 | 2026-10-25 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-12-01 | Not Started | 36
Actual
5 | 0050 | Fire protection & sprinklers | CT | 2.1 | Medium | Planned | 2026-10-28 | 2026-11-07 | 2026-11-14 | 2026-11-28 | 2026-12-05 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-20 | Not Started | 108
Actual
6 | 0060 | BMS / ELV / security systems | CT | 1.8 | Medium | Planned | 2026-12-15 | 2026-12-22 | 2026-12-26 | 2027-01-05 | 2027-01-12 | 2027-01-12 | 2027-01-16 | 2027-01-20 | 2027-01-24 | 2027-01-31 | 2027-02-10 | Not Started | 156
Actual
7 | 0070 | Roofing & waterproofing | CT | 1.6 | High | Planned | 2026-08-24 | 2026-08-31 | 2026-09-04 | 2026-09-14 | 2026-09-21 | 2026-09-21 | 2026-09-25 | 2026-09-29 | 2026-10-03 | 2026-10-10 | 2026-10-20 | Not Started | 43
Actual
8 | 0080 | Common-area fit-out & finishes | CT | 4 | Medium | Planned | 2026-12-07 | 2026-12-17 | 2026-12-24 | 2027-01-07 | 2027-01-14 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-03-01 | Not Started | 148
Actual
9 | 0090 | Ceilings & partitions | CT | 1.4 | Medium | Planned | 2027-01-17 | 2027-01-24 | 2027-01-28 | 2027-02-07 | 2027-02-14 | 2027-02-14 | 2027-02-18 | 2027-02-22 | 2027-02-26 | 2027-03-05 | 2027-03-15 | Not Started | 189
Actual
10 | 0100 | Soft & hard landscaping | CT | 0.9 | Low | Planned | 2027-03-05 | 2027-03-12 | 2027-03-16 | 2027-03-26 | 2027-04-02 | 2027-04-02 | 2027-04-06 | 2027-04-10 | 2027-04-14 | 2027-04-21 | 2027-05-01 | Not Started | 236
Actual
11 | 0110 | Car-park equipment & wayfinding signage | NQ | 0.6 | Low | Planned | 2027-02-17 | 2027-02-24 | 2027-02-28 | 2027-03-10 | 2027-03-17 | 2027-03-17 | 2027-03-21 | 2027-03-25 | 2027-03-29 | 2027-04-05 | 2027-04-15 | Not Started | 220
Actual
12 | 0120 | Sanitaryware & washroom fit-out | NQ | 0.8 | Medium | Planned | 2026-12-25 | 2027-01-01 | 2027-01-05 | 2027-01-15 | 2027-01-22 | 2027-01-22 | 2027-01-26 | 2027-01-30 | 2027-02-03 | 2027-02-10 | 2027-02-20 | Not Started | 166
Actual
13 | 0130 | Structured cabling / IT infrastructure | CT | 1.2 | Medium | Planned | 2027-01-12 | 2027-01-19 | 2027-01-23 | 2027-02-02 | 2027-02-09 | 2027-02-09 | 2027-02-13 | 2027-02-17 | 2027-02-21 | 2027-02-28 | 2027-03-10 | Not Started | 184
Actual
14 | 0140 | Specialist feature lighting (proprietary) | SS | 0.45 | Low | Planned | 2027-02-26 | 2027-03-02 | 2027-03-02 | 2027-03-09 | 2027-03-13 | 2027-03-13 | 2027-03-13 | 2027-03-17 | 2027-03-21 | 2027-03-28 | 2027-04-05 | Not Started | 229
Actual
15 | 0150 | Loading-dock equipment (levellers & shutters) | NQ | 0.55 | Low | Planned | 2027-02-22 | 2027-03-01 | 2027-03-05 | 2027-03-15 | 2027-03-22 | 2027-03-22 | 2027-03-26 | 2027-03-30 | 2027-04-03 | 2027-04-10 | 2027-04-20 | Not Started | 225
Actual
Planned
Actual
Planned
Actual
Planned
Actual
Formulas:
Prep Bid Docs = IF(OR([Required On Site]="",[Proc Route]=""),"",[Required On Site]-ROUND(INDEX(Configuration!$B17:F17,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Float RFP = IF([Prep Bid Docs]="","",[Prep Bid Docs]+ROUND(INDEX(Configuration!$B7:F7,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Bid Period = IF([Float RFP]="","",[Float RFP]+ROUND(INDEX(Configuration!$B8:F8,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Bid Review = IF([Bid Period]="","",[Bid Period]+ROUND(INDEX(Configuration!$B9:F9,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Inter- views = IF([Bid Review]="","",[Bid Review]+ROUND(INDEX(Configuration!$B10:F10,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Technical Eval = IF([Inter- views]="","",[Inter- views]+ROUND(INDEX(Configuration!$B11:F11,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Approval / Award = IF([Technical Eval]="","",[Technical Eval]+ROUND(INDEX(Configuration!$B12:F12,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Issue PO = IF([Approval / Award]="","",[Approval / Award]+ROUND(INDEX(Configuration!$B13:F13,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Issue Contract = IF([Issue PO]="","",[Issue PO]+ROUND(INDEX(Configuration!$B14:F14,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Mobili- sation = IF([Issue Contract]="","",[Issue Contract]+ROUND(INDEX(Configuration!$B15:F15,1,IF([Proc Route]="SS",5,IF([Proc Route]="NQ",4,IF([Est Value ($M)]>=30,1,IF([Est Value ($M)]>=5,2,IF([Est Value ($M)]>=2,3,4))))))*7/5,0))
Float (Days) = IF([Prep Bid Docs]="","",[Prep Bid Docs]-TODAY())

## Dashboard
PROCUREMENT TRACKER --- Northgate Retail Centre, Meridian Land development
Date: 12 Jul 2026 ¦ From: Apex Project Management ¦ Project: Northgate Retail Centre ¦ Ref: NGRC-PT-001 ¦ Value: $68M (construction)
AUTO-POPULATED from Procurement Schedule. Do not edit. All data flows from the Schedule tab.
PORTFOLIO SUMMARY
Total Packages |  | Awarded |  | In Progress |  | Not Started |  | On Hold |  | At Risk |  | Behind Prog. |  | On Track
15 |  | 0 |  | 2 |  | 13 |  | 0 |  | 2 |  | 0 |  | 13
PACKAGE SUMMARY
Approval: >$30M = Board ¦ $5M-$30M = Committee ¦ $2M-$5M = Proc Head ¦ <$2M = Proc Manager --- Delta: + = late (red) ¦ 0 = on time ¦ - = early (green)
RAG: Red = procurement start date has passed ¦ Amber = <30 days until procurement must start ¦ Green = 30+ days ¦ N/A = awarded/complete
[6 empty] | PROCUREMENT START |  |  | AWARD / CONTRACT
WP# | Package Description | Proc Route | Est. Value ($M) | Approval Level | Required On Site | Planned Proc Start | Actual Proc Start | Start Delta (Days) | Planned Award | Actual Award | Award Delta (Days) | Status | Priority | Float (Days) | RAG
0010 | Structural steel - transfer slab & primary frame | CT | 4.2 | Proc Head | 2026-09-15 | 2026-06-23 | 2026-06-28 | 5 | 2026-08-11 |  |  | In Progress | High | -19 | Red
0020 | Facade & unitised curtain wall | CT | 6.8 | Committee | 2026-10-05 | 2026-06-21 | 2026-06-18 | -3 | 2026-08-29 |  |  | In Progress | High | -21 | Red
0030 | Lifts & escalators | CT | 3.5 | Proc Head | 2027-01-15 | 2026-10-23 |  |  | 2026-12-11 |  |  | Not Started | High | 103 | Green
0040 | MEP services (mechanical, electrical, plumbing) | CT | 8.5 | Committee | 2026-12-01 | 2026-08-17 |  |  | 2026-10-25 |  |  | Not Started | High | 36 | Green
0050 | Fire protection & sprinklers | CT | 2.1 | Proc Head | 2027-01-20 | 2026-10-28 |  |  | 2026-12-16 |  |  | Not Started | Medium | 108 | Green
0060 | BMS / ELV / security systems | CT | 1.8 | Proc Manager | 2027-02-10 | 2026-12-15 |  |  | 2027-01-16 |  |  | Not Started | Medium | 156 | Green
0070 | Roofing & waterproofing | CT | 1.6 | Proc Manager | 2026-10-20 | 2026-08-24 |  |  | 2026-09-25 |  |  | Not Started | High | 43 | Green
0080 | Common-area fit-out & finishes | CT | 4 | Proc Head | 2027-03-01 | 2026-12-07 |  |  | 2027-01-25 |  |  | Not Started | Medium | 148 | Green
0090 | Ceilings & partitions | CT | 1.4 | Proc Manager | 2027-03-15 | 2027-01-17 |  |  | 2027-02-18 |  |  | Not Started | Medium | 189 | Green
0100 | Soft & hard landscaping | CT | 0.9 | Proc Manager | 2027-05-01 | 2027-03-05 |  |  | 2027-04-06 |  |  | Not Started | Low | 236 | Green
0110 | Car-park equipment & wayfinding signage | NQ | 0.6 | Proc Manager | 2027-04-15 | 2027-02-17 |  |  | 2027-03-21 |  |  | Not Started | Low | 220 | Green
0120 | Sanitaryware & washroom fit-out | NQ | 0.8 | Proc Manager | 2027-02-20 | 2026-12-25 |  |  | 2027-01-26 |  |  | Not Started | Medium | 166 | Green
0130 | Structured cabling / IT infrastructure | CT | 1.2 | Proc Manager | 2027-03-10 | 2027-01-12 |  |  | 2027-02-13 |  |  | Not Started | Medium | 184 | Green
0140 | Specialist feature lighting (proprietary) | SS | 0.45 | Proc Manager | 2027-04-05 | 2027-02-26 |  |  | 2027-03-13 |  |  | Not Started | Low | 229 | Green
0150 | Loading-dock equipment (levellers & shutters) | NQ | 0.55 | Proc Manager | 2027-04-20 | 2027-02-22 |  |  | 2027-03-26 |  |  | Not Started | Low | 225 | Green

## Issues & Risks
PROCUREMENT RISK REGISTER --- Northgate Retail Centre, Meridian Land development
Date: 12 Jul 2026 ¦ From: Apex Project Management ¦ Ref: NGRC-PT-001-RISK ¦ Construction Manager: James Okafor
# | WP# | Package | Risk Type | Risk Description | Impact | Likelihood | Priority | Mitigation | Owner | Due Date | Status
1 | 0020 | Facade & curtain wall | Cost | Lowest bidder (BuildRight Facades) carries scope gaps on cill flashings and movement joints; risk of post-award variation. | High | Medium | High | Level pricing against Vertex Envelope scope; close gaps in pre-award clarification before recommendation to award. | Daniel Cross | 2026-07-17 | In Progress
2 | 0010 | Structural steel | Schedule | Level 3 transfer-slab design 2 weeks late from FormWorks; steel fabrication release cannot lock until design frozen. Slab pour on critical path. | High | High | High | Escalate design freeze with FormWorks; issue advance-order for primary tonnage against 90% design to protect fabrication slot. | James Okafor | 2026-07-18 | In Progress
3 | 0070 | Roofing & waterproofing | Design | Basement waterproofing variation (~$180k) under review; spec revision may cascade to roofing package scope and pricing basis. | Medium | Medium | Medium | Freeze waterproofing spec before roofing RFP floats; dispute ~$70k of the variation with Cornerstone before tender basis is set. | Daniel Cross | 2026-07-24 | Not Started
4 | 0040 | MEP services | Schedule | Long-lead switchgear (16-20 wk delivery) sits inside the procurement window; late award pushes energisation past fit-out start. | High | Medium | High | Pull MEP RFP forward 3 weeks; pre-order switchgear on nominated-supplier basis ahead of main MEP award. | James Okafor | 2026-08-07 | Not Started
5 | 0030 | Lifts & escalators | Schedule | Single-source OEM lead times up to 22 weeks; competitive tender window may not leave enough float before required-on-site. | Medium | Medium | Medium | Confirm delivery lead times at RFP stage; consider negotiated route if tender float proves insufficient. | James Okafor | 2026-09-30 | Not Started

## Configuration
CONFIGURATION --- Procurement Duration Settings
Stage durations drive the auto-calculation on the Procurement Schedule. Edit these to change all planned dates.
STANDARD PROCUREMENT STAGE DURATIONS (Working Days)
Stage | CT (>$5M) | CT ($2-5M) | CT (<$2M) | NQ (<$2M) | SS
Prep Bid Docs | 10 | 10 | 7 | 5 | 3
Float RFP | 5 | 5 | 5 | 3 | 0
Bid Period | 15 | 15 | 10 | 7 | 5
Bid Review | 10 | 7 | 5 | 5 | 3
Interviews | 5 | 5 | 3 | 0 | 0
Technical Eval | 10 | 7 | 5 | 3 | 0
Approval / Award | 10 | 7 | 5 | 3 | 3
Issue PO | 5 | 5 | 5 | 3 | 3
Issue Contract | 5 | 5 | 5 | 5 | 5
Mobilisation | 10 | 10 | 10 | 7 | 5
TOTAL (Working Days) | 85 | 76 | 60 | 41 | 27
TOTAL (Calendar Weeks, approx) | 17 | 15 | 12 | 8 | 5
WARNING: Rows 7-16 are referenced by the auto-calc formulas on the Procurement Schedule. Do not insert or delete rows in this section.
APPROVAL THRESHOLDS
Threshold | Amount | Approver | Notes
High Value | >$30M | Tender Board | Full board review. Chair: Client rep. Members: Proc Head, PM Director, cost consultant.
Mid Value | $5M - $30M | Procurement Committee | Committee review. Shorter lead time; still needs scheduling.
Low Value | $2M - $5M | Procurement Head | Direct approval.
Minor | <$2M | Procurement Manager | Direct approval.
PROJECT INFORMATION
Project Name | Northgate Retail Centre
Location | Meridian Land development
Project Reference | NGRC-PT-001
Estimated Value | $68M (construction)
Construction Manager | James Okafor
Prepared By | Apex Project Management
Date Created | 12 Jul 2026