## Slide 1
NORTHGATE RETAIL CENTRE
CONSTRUCTION MASTER PROGRAMME
Baseline Issue | Rev 0 | Progress update — Month 9 of 22
Prepared by: Daniel Cross | Project Director, Apex Project Management
Client / Developer: Meridian Land Main Contractor: Cornerstone Construction
Apex Project Management | Construction Management

## Slide 2
NORTHGATE RETAIL CENTRE
Master Programme — High Level
Page 1 of 3
Q1 2025
Q2 2025
Q3 2025
Q4 2025
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Jan
Mar
May
Jul
Sept
Nov
Jan
Mar
May
Jul
Sept
Nov
▼ TODAY
TASK / ACTIVITY
DURATION
START
FINISH
ENABLING WORKS & SITE ESTABLISHMENT
87d
03 Feb 25
30 Apr 25
Site Possession / NTP
0d
03 Feb 25
03 Feb 25
SUBSTRUCTURE — PILING & BASEMENT
214d
01 Apr 25
31 Oct 25
Basement Slab Complete
0d
31 Oct 25
31 Oct 25
SUPERSTRUCTURE — RC FRAME
243d
15 Sept 25
15 May 26
L3 Transfer Slab Pour ◀ CRITICAL
0d
30 Jan 26
30 Jan 26
Topping Out
0d
15 May 26
15 May 26
FAÇADE & EXTERNAL ENVELOPE
183d
02 Mar 26
31 Aug 26
MEP INSTALLATION
241d
02 Feb 26
30 Sept 26
INTERNAL FIT-OUT
152d
01 Jun 26
30 Oct 26
TESTING & COMMISSIONING
51d
01 Oct 26
20 Nov 26
HANDOVER & PRE-OPENING
27d
01 Nov 26
27 Nov 26
Practical Completion
0d
27 Nov 26
27 Nov 26
OPENING — November 2026
0d
30 Nov 26
30 Nov 26
Summary phase
Activity
Gate milestone
Opening
Today
Apex Project Management | Construction Management
Baseline Programme | Rev 0 | Oct 2025 update | Page 1 of 3

## Slide 3
NORTHGATE RETAIL CENTRE
Substructure & Superstructure
Page 2 of 3
Q1 2025
Q2 2025
Q3 2025
Q4 2025
Q1 2026
Q2 2026
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
▼ TODAY
TASK / ACTIVITY
DURATION
START
FINISH
ENABLING WORKS
87d
03 Feb 25
30 Apr 25
Site Clearance & Hoarding
26d
03 Feb 25
28 Feb 25
Utilities Diversion
43d
17 Feb 25
31 Mar 25
Piling Platform & Setup
38d
24 Mar 25
30 Apr 25
SUBSTRUCTURE
214d
01 Apr 25
31 Oct 25
Bored Piling
67d
01 Apr 25
06 Jun 25
Bulk Excavation & Shoring
68d
12 May 25
18 Jul 25
Pile Caps & Ground Beams
61d
30 Jun 25
29 Aug 25
Basement Raft Slab
47d
04 Aug 25
19 Sept 25
Basement Walls & B1 Slab
54d
08 Sept 25
31 Oct 25
Basement Slab Complete
0d
31 Oct 25
31 Oct 25
SUPERSTRUCTURE — RC FRAME
243d
15 Sept 25
15 May 26
Ground–L2 Columns & Slabs
117d
15 Sept 25
09 Jan 26
L3 Transfer Slab — Formwork & Rebar
25d
05 Jan 26
29 Jan 26
L3 Transfer Slab Pour ◀ GATE
0d
30 Jan 26
30 Jan 26
L3–Roof Columns & Slabs
82d
02 Feb 26
24 Apr 26
Roof Slab & Stair/Lift Cores
40d
06 Apr 26
15 May 26
Topping Out
0d
15 May 26
15 May 26
Summary phase
Activity
Gate milestone
Opening
Today
Apex Project Management | Construction Management
Baseline Programme | Rev 0 | Oct 2025 update | Page 2 of 3

## Slide 4
NORTHGATE RETAIL CENTRE
Façade, MEP, Fit-out & Handover
Page 3 of 3
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
TASK / ACTIVITY
DURATION
START
FINISH
FAÇADE & EXTERNAL ENVELOPE
183d
02 Mar 26
31 Aug 26
Curtain Wall / Cladding Install
117d
06 Apr 26
31 Jul 26
Roofing & Waterproofing
54d
04 May 26
26 Jun 26
Storefront & Glazing
78d
15 Jun 26
31 Aug 26
Building Watertight
0d
31 Aug 26
31 Aug 26
MEP INSTALLATION
241d
02 Feb 26
30 Sept 26
1st Fix — Risers & Containment
103d
02 Feb 26
15 May 26
Plant & Equipment Install
117d
06 Apr 26
31 Jul 26
2nd Fix & Terminations
122d
01 Jun 26
30 Sept 26
INTERNAL FIT-OUT
152d
01 Jun 26
30 Oct 26
Mall Common Area Fit-out
122d
01 Jun 26
30 Sept 26
Lifts & Escalators
93d
15 Jun 26
15 Sept 26
Tenant Shell Handover
91d
01 Aug 26
30 Oct 26
TESTING & COMMISSIONING
51d
01 Oct 26
20 Nov 26
Integrated Systems T&C
37d
01 Oct 26
06 Nov 26
Fire & Life Safety Certification
32d
20 Oct 26
20 Nov 26
Occupancy Permit ◀ GATE
0d
20 Nov 26
20 Nov 26
HANDOVER & PRE-OPENING
27d
01 Nov 26
27 Nov 26
Snagging & De-snag
24d
01 Nov 26
24 Nov 26
Client Handover & O&M
18d
10 Nov 26
27 Nov 26
Practical Completion
0d
27 Nov 26
27 Nov 26
OPENING — November 2026
0d
30 Nov 26
30 Nov 26
Summary phase
Activity
Gate milestone
Opening
Today
Apex Project Management | Construction Management
Baseline Programme | Rev 0 | Oct 2025 update | Page 3 of 3